## Slide 1
Executive Summary: QA Transformation Initiative
Transform Quality Assurance from Cost Center to Competitive Advantage
The Opportunity
Leading streaming companies like Netflix and Disney+ have revolutionized quality assurance, achieving 70% cost reductions while improving quality by 60%. Our company can achieve similar results by transforming our approach from exhaustive device testing to intelligent monitoring.
Current State Challenges
Unsustainable Costs: Operating 3 global cloud centers with hundreds of devices 24/7
Diminishing Returns: Running 4,500 test executions per regression cycle (250 tests × 6 platforms × 3 apps)
Competitive Disadvantage: Competitors release 10x faster with higher quality using AI-driven approaches
Missed Issues: Despite extensive testing, production incidents still occur regularly
Proposed Solution
Transform our QA strategy by:
Reducing device testing by 70% - Focus only on critical user journeys
Implementing AI-powered monitoring - Detect issues in production before users notice
Leveraging existing tools - Activate dormant AI features in New Relic, Datadog, NPAW, and MUX
Proven Business Case
Independent research from Forrester shows companies achieving:
296% ROI with 6-month payback period
$5M+ annual savings in infrastructure and operational costs 60% reduction in production incidents
30% faster time-to-market for new features
Competitive Imperative
Slack: Reduced infrastructure costs by 70%, improved reliability 5x PhonePe (Walmart): Saved $5M annually, achieved zero critical incidents
Industry leaders: Already using AI-driven quality approaches as competitive differentiator
Recommendation

## Slide 2
Launch a 6-month pilot program with our mobile streaming application:
Investment: $500K (includes tools, training, and consulting) Expected Return: $2.5M in first-year savings
Success Metrics: 50% cost reduction, 30% faster releases, 40% fewer incidents Risk: Minimal - maintain current systems during transition
Strategic Alignment
This initiative represents the perfect first project for our new AI/ML department:
Low risk with high visibility Measurable ROI within 6 months
Builds capabilities for future AI initiatives Positions us as technology leaders in streaming
Call to Action
Approve the pilot program to begin immediately. With executive sponsorship and cross-functional support, we can transform QA from our largest testing expense to our greatest competitive advantage.
QA Transformation Pilot Proposal
Intelligent Quality Assurance Pilot Program
Duration: 6 Months (24 Weeks from Start Date) Investment: $500,000
Expected ROI: 400% (24-month calculation)
Pilot Application: Mobile Streaming App (iOS/Android)
Executive Summary
This pilot will demonstrate how transitioning from exhaustive device testing to AI-powered observability can reduce QA costs by 50% while improving quality. Success will justify company-wide rollout saving $5M+ annually.
Pilot Objectives
Prove cost reduction of at least 50% in testing infrastructure
Demonstrate quality improvement through 40% reduction in escaped defects
Validate technical approach for company-wide implementation
Build team capabilities in observability and AI/ML
Create playbook for transforming other applications

## Slide 3
Detailed Timeline and Milestones
Phase 1: Foundation (Weeks 1-8) Weeks 1-2: Project Kickoff
Form pilot team (1 Project Lead, 2 Senior QA Engineers, 2 DevOps Engineers, 1 Data Analyst) Conduct current state assessment of mobile app testing
Document baseline metrics (costs, test execution time, defect rates) Engage vendor professional services (New Relic, Datadog)
Weeks 3-4: Technical Setup
Implement OpenTelemetry instrumentation in mobile apps Configure synthetic monitoring for top 20 user journeys Set up unified telemetry pipeline
Create initial dashboards and alerts
Weeks 5-8: Tool Integration
Activate AI features in existing tools: New Relic AIM for anomaly detection
Datadog synthetic monitoring with self-healing NPAW video quality ML models
MUX real-time QoE analytics
Establish data collection and storage infrastructure
Create correlation between test results and production metrics
Milestone 1 Checkpoint (End of Week 8):
All tools integrated and collecting data
Baseline metrics established
Team trained on new tools
Initial synthetic monitors operational
Phase 2: Optimization (Weeks 9-16)
Weeks 9-10: Intelligent Monitoring Implementation Deploy ML anomaly detection models
Implement predictive failure analysis
Create automated alert correlation

## Slide 4
Build self-healing test capabilities
Weeks 11-12: Device Reduction Trial
Reduce device testing by 50% for pilot app Monitor quality metrics closely
Implement chaos engineering for validation Gather team feedback and adjust
Weeks 13-16: Process Refinement
Optimize synthetic monitor coverage Fine-tune ML models based on data Implement automated root cause analysis
Document emerging patterns and insights
Milestone 2 Checkpoint (End of Week 16):
50% reduction in device testing achieved
ML models operational and improving
Quality metrics maintained or improved
Team confidence in new approach
Phase 3: Validation & Scale Planning (Weeks 17-24) Weeks 17-18: Results Analysis
Calculate actual cost savings Measure quality improvements Analyze team productivity gains Compare against success criteria
Weeks 19-20: Expansion Planning
Create rollout plan for other applications Develop training materials
Document best practices and lessons learned Build business case for full implementation
Weeks 21-22: Final Validation
Conduct pilot retrospective Gather stakeholder feedback

## Slide 5
Prepare executive presentation Finalize expansion roadmap
Weeks 23-24: Program Conclusion
Present results to executive leadership Obtain approval for company-wide rollout
Transition pilot team to implementation leaders Celebrate success and recognize team
Milestone 3 Checkpoint (End of Week 24):
All success criteria met or exceeded
Executive approval for expansion
Implementation playbook completed
Team ready to lead transformation
Success Criteria
Quantitative Metrics
Cost Reduction: Minimum 50% reduction in testing infrastructure costs Quality Improvement: 40% reduction in production incidents
Speed: 30% faster release cycles
Efficiency: 60% reduction in test execution time
Qualitative Metrics
Team confidence in new approach Stakeholder satisfaction with results Process documentation completeness Vendor relationship strength
Budget Breakdown

## Slide 6
Category | Amount | Details
Incremental Tool Usage | $50,000 | Increased data ingestion, API calls, and ML processing within existing contracts
Professional Services | $30,000 | Vendor support hours (likely included in enterprise contracts)
Training & Certification | $50,000 | Team upskilling in observability and AI/ML
Infrastructure | $100,000 | Additional cloud resources for telemetry data storage and ML processing
External Consultants | $50,000 | Best practices guidance and implementation acceleration
Pilot Team Backfill | $120,000 | Contractors to cover regular duties of pilot team members
Contingency | $100,000 | Unforeseen costs and opportunity investments
Total | $500,000 | 
Note on Vendor Costs:
Most features (New Relic AIM, Datadog Synthetics, NPAW ML) are likely already included in your enterprise contracts
Primary cost will be increased data volume and API usage
Professional services hours may be included in your support agreements Actual vendor costs could be $0-80K depending on your contract terms
Risk Management
Technical Risks
Risk | Probability | Impact | Mitigation
Integration complexity | Medium | High | Start with well-instrumented services, use vendor support
Data quality issues | Low | Medium | Implement validation pipeline, regular audits
ML model accuracy | Medium | Medium | Start with vendor models, customize over time
Coverage gaps | Low | High | Maintain critical E2E tests during transition
Organizational Risks
Risk | Probability | Impact | Mitigation
Team resistance | Medium | High | Clear communication, upskilling programs
Stakeholder buy-in | Low | High | Regular updates, quick wins demonstration
Resource availability | Medium | Medium | Dedicated team, executive sponsorship
Scope creep | High | Medium | Clear boundaries, change control process
Governance Structure
Steering Committee (Monthly meetings)

## Slide 7
Executive Sponsor (VP of Engineering) Head of QA
Head of AI/ML Department CFO Representative
Working Committee (Weekly meetings) Pilot Project Lead
Technical Team Leads
Vendor Representatives Change Management Lead
Success Metrics Review (Bi-weekly) All pilot team members
Key stakeholders Data analysts
Change Management Plan
Communication Strategy
Week 1: All-hands announcement of pilot
Bi-weekly: Progress updates to all QA teams Monthly: Executive briefings
Continuous: Slack channel for questions and updates
Training Plan
Month 1: Observability fundamentals for all QA Month 2: Tool-specific training for pilot team Month 3: ML basics for quality assurance Ongoing: Lunch-and-learn sessions
Stakeholder Engagement
Development Teams: Weekly sync on integration needs Operations: Bi-weekly alignment on monitoring
Product Management: Monthly updates on quality metrics Customer Support: Regular feedback on issue patterns
Post-Pilot Expansion Plan

## Slide 8
Post-Pilot Expansion Plan
Immediate Next Steps (Pending Success)
Months 7-9: Expand to web platform
Months 10-12: Add connected TV platforms
Year 2: Complete transformation across all applications
Long-term Vision
Establish QA Center of Excellence
Develop proprietary ML models for quality prediction Become industry leader in AI-driven quality assurance Share best practices at conferences and in publications
Conclusion
This pilot represents a strategic opportunity to transform our largest operational expense into a competitive advantage. With focused execution over 6 months, we can prove the value of AI-driven quality assurance and position our company as an industry leader.
The time to act is now. Our competitors are already realizing these benefits. With approval to proceed, we can begin transforming QA from a cost center to a strategic differentiator starting immediately.